## Sheet1
Page | Feedback | Priority | Comments |  | Dupe's Responses
Create Account | Still need to remove the City dropdown since we have location turned on | Medium |  | Done
Create Account | Updated language for password setting (make sure spaces are included: Password must include: uppercase, lowercase, number, and special character | High |  | Done
Personal Info - Select Questions | Questions aren’t updated with the latest file that I uploaded on the portal. Please use that as it has grammatical changes, etc | High |  | Done
Personal Info - Select Questions | For what are your love languages (allow the user to select at least 2) | Low
Personal Info - Select Questions | Update the language op top. Bold: Respond to at least 2 questions and a maximum of 5. Character limit is 500 (medium) | Low |  | Done
Personal Info | Alphabetical order for Origins: Afro-Caribbean, Afro-Latino, Black / African-America, East African, Sub-Saharan African, West African | Low |  | Done
Personal Info | When I try to link my Instagram it throws an error message. Not sure if that is because it is in beta | High | Only if this is an actuall issue butit if it is because of beta ignore priority | Its because of beta | Thanks for confirming
Photos | Update Language: Upload a minimum of 3 and a maximum of 7 | Low |  | Done
Photos | Facebook I got an error message as well. Sounds like because I am in beta mode, which is ok. | High | Only if this is an actuall issue butit if it is because of beta ignore priority | Because of beta | Thanks for confirming
Photos | The app crashed twice while trying to upload photos (literally just blanked and took me back to where I would have to click on it. I was playing with the rotation option. Basically any time I tried to touch, change or, resize it crashed, | High | If nothing else gets fixed before Monday this is where I need all the attention to go | This is fixed
Photos | As you rotate the picture, it seems to narrow the width and length of the picture. I don’t want that to happen | High |  | This is fixed
Photos | Overall: photo length will work. But the ratios still do not match Instagram because the pictures I selected, I would be able to see my full shoes AND screen uptop and I could not achieve that in the app | Medium |  | This needs time. | That works. Possible for early March?
Photos | I would like to be able to rearrange the order my pics by dragging and dropping | Medium
Photos | Interesting thing happened that didn’t happen before. As soon as I hit upload for my photos it took me to matching. It did not, make me hit submit or anything. Which means I didn’t get to add in preferences | High |  | Earlier we made the user to reach the prefernce screen to submit, but it was mentioned that its not necessary so need not to redeirect user to preference. So we changed that. | Agreed, I definitely don't want to force soemone to add preferences. But after adding my photos and hitting upload it just went straight to matches. I think we need to still aloow people to preview their profile before they submit it to start matching. let me know if I am explaining that well. Basically, I don't want upload of photos to trigger an active profile. I want someone to be able to review their details again and then hit submit
Settings - Customer Service | Customer Service. Here is the thank you language I provided, Please update: Thanks for your inquiry! A member of our team will respond in 48 hours. | Medium
Settings | Remove FAQ section | Medium
Settings - Feedback | Feedback. Here is what I wanted for the feedback section: I would give them the 5 star rating option and then free text (150 character or less) that they can provide feedback. Is there a way to have it automatically integrate with Android and Apple app stores? | Medium
Settings - Profile Standout | Language provided for make your profile standout and safety tips is not included. Adding here for reference. | Medium
Settings - Profile Standout | We are here to help you optimize your assets and make your experience on Black Social successful. Here are some quick tips. - Share photos that show your personality and best features. Not just selfies and groupshots. Choose various angles, full body shots, and make sure your face isn’t covered - Help people see your personality answering questions. It makes it easier to break the ice and indicates things you may have in common - Be honest! Matching works best when you are honest with yourself and us | Medium
Settings - Safety Tips | Safety Tips. Let’s just call it Safety | Medium
Settings - Safety Tips | Black Social aims to create a safe and secure space for all users. We will do all we can to ensure our platform is secure for all users. It is important that all users use their best judgment and take the necessary precautions to protect themselves. You cannot control what others do, but you can take steps to make sure that you are safe and protected. Below are some tips to ensure you have a great experience while using Black Social. - Protect Your Personal Information - Do not share Financial Details - Stay on the Platform - Be wary of users who will not phone / video chat - Report suspicious or offensive behavior | Medium
Settings | The delete account button doesn’t work | Medium
Profile | This is really small but the picture I upload that is my main picture, should not repeat after all of my information. | Medium
Profile | Also, small if I don’t provide information (e.g. no info on drinker, smoker or weed) is it possible to have that just not appear? | Low
Profile - Preferences | Preference options are still not saving. And I think I just figured out why after checking. You have to scroll down to see the submit button and you don’t know it’s there. With all that white space can we move the submit button up so it is visible on the page without scrolling. Can we check this everywhere. | High |  | Done
Profile - Preferences | Make sure when I select preference options there is a comma and then a space before the next work. Example Jewish, Christian, Islam | Medium
My Account | Let’s remove country / region | Low
My Account | I don’t think we need the upload photo option from my account | Low
Saved Profiles | Can we say that they will disappear after 24 hours. | Medium
Overall | If a screen has a lot of white space and the submit button requires scroll, we need to move up the submit button so you don't have to scroll | High |  | Done